## Sheet1
Date:16th aug to 30th aug2024
Team Leader: | Varsha Raut
Team Member: | Nabha Chitnis
Sr.no | Project Name | Activity | Description | Estimated hours | Actual hours | Remarks/Blockers
1 | HHC Aggrigation | testing | service creation- All field | 10 | 8 | Server is not working some time I had to wait until the devloper solved the issues.
|  |  | Enquiry- web form/community and HD | 7 | 8
|  |  | ongoing service | 10 | 10
|  |  | APP testing (professional App and community APP) | 10 | 15
|  |  | multiple allocation functionality | 7 | 10
|  |  | end to end testing | 10 | 10